STATEMENT OF WORK

Cloud Platform Architecture

& Execution Blueprint

Proxmox + ZeroTier–based Hyperscale Cloud Alternative

CONFIDENTIAL

| Document Version: | 1.0 |
| --- | --- |
| Date: | January 11, 2026 |
| Prepared By: | Infinititech Partners |
| Project Code: | CLOUD-PLATFORM-2025 |

# Table of Contents

Table of Contents	2

1. Executive Summary	4

2. Project Overview	4

2.1 Project Description	4

2.2 Project Objectives	4

2.3 Core Design Principles	5

3. Scope of Work	6

3.1 In-Scope Deliverables	6

3.2 Out-of-Scope Items	6

4. Feature Specifications	7

4.1 User Dashboard - Tenant Control Plane	7

4.1.1 Identity & Organization Management	7

4.1.2 Compute Services	7

4.1.3 Container & Kubernetes Services	7

4.1.4 Networking	8

4.1.5 Storage Services	8

4.1.6 Platform Services	9

4.1.7 Observability & Billing	9

4.2 Super Admin Dashboard - Cloud Operator Plane	10

4.2.1 Global Tenant Management	10

4.2.2 Data Center Management	10

4.2.3 Proxmox Cluster Management	10

4.2.4 Network Fabric Control	11

4.2.5 Storage Backend Control	12

4.2.6 Security & Compliance	12

4.2.7 Platform Operations	12

4.2.8 Financial & Metering Oversight	12

5. Technical Architecture	14

5.1 Architecture Overview	14

5.2 System Layers	14

5.3 Control Plane Services	14

6. Data Flow Design	16

6.1 High-Level Data Flow	16

6.2 VM Creation Flow	16

6.3 Billing Data Flow	17

6.4 Failure Handling	17

7. Technology Stack	18

7.1 Backend Services	18

7.2 Infrastructure Layer	18

7.3 State Management & Coordination	18

7.4 Security Stack	19

7.5 Observability Stack	19

7.6 Frontend Stack	19

7.7 DevOps & Automation	20

8. Project Phases & Milestones	21

8.1 Phase Overview	21

8.2 Phase 1: Foundation (Weeks 1-12)	21

8.3 Phase 2: Control Plane (Weeks 13-28)	21

8.4 Phase 3: User Experience (Weeks 29-38)	22

8.5 Phase 4: Platform Services (Weeks 39-50)	23

8.6 Phase 5: Production Readiness (Weeks 51-58)	23

8.7 Phase 6: Launch & Stabilization (Weeks 59-64)	23

9. Deliverables Summary	25

10. Assumptions & Dependencies	26

10.1 Assumptions	26

10.2 Dependencies	26

10.3 Risks & Mitigations	26

11. Acceptance Criteria	28

11.1 Functional Acceptance	28

11.2 Performance Acceptance	28

11.3 Security Acceptance	28

11.4 Documentation Acceptance	28

12. Terms & Conditions	30

12.1 Change Control	30

12.2 Intellectual Property	30

12.3 Warranty	30

12.4 Confidentiality	30

# 1. Executive Summary

This Statement of Work defines the comprehensive development of a next-generation cloud infrastructure platform designed to compete with major cloud providers while leveraging cost-effective, enterprise-grade technologies. The platform combines Proxmox VE virtualization with ZeroTier software-defined networking to create a distributed, multi-datacenter cloud infrastructure.

The solution delivers two distinct operational planes: a Tenant Control Plane providing customers with isolated cloud environments featuring compute, storage, networking, and managed services, and a Cloud Operator Plane enabling super administrators to manage the entire infrastructure fabric including datacenters, clusters, and global operations.

Key Business Objectives

- Deliver enterprise-grade cloud services at 40-60% lower cost than hyperscale alternatives

- Enable rapid multi-datacenter deployment with software-defined networking

- Provide complete tenant isolation with zero infrastructure exposure

- Support managed Kubernetes, databases, and serverless compute

- Ensure security-first architecture with comprehensive audit capabilities

# 2. Project Overview

## 2.1 Project Description

The Cloud Platform project encompasses the design, development, and deployment of a complete Infrastructure-as-a-Service and Platform-as-a-Service solution. Built on proven open-source technologies including Proxmox VE, ZeroTier, Kubernetes, and Ceph, the platform provides a modern alternative to traditional cloud providers.

The architecture follows a declarative, control-plane-centric design where all infrastructure operations flow through a centralized control plane that maintains desired state and continuously reconciles with actual infrastructure state.

## 2.2 Project Objectives

- Build a multi-tenant cloud platform with complete resource isolation

- Implement unified control plane for all infrastructure operations

- Deploy software-defined networking across geographically distributed datacenters

- Create intuitive dashboards for both tenants and operators

- Establish comprehensive billing and metering infrastructure

- Ensure production-grade security, observability, and reliability

## 2.3 Core Design Principles

| Principle | Description |
| --- | --- |
| Single Source of Truth | Control Plane database holds all authoritative state |
| Declarative Intent | Desired state stored and reconciled continuously |
| No Direct UI Calls | All UI operations route through API Gateway to Control Plane |
| Complete Auditability | Every action logged with full context and attribution |
| Scope-Based Security | Same APIs for users and admins, enforced by authorization scope |
| Failure Tolerance | Automatic retries, rollbacks, and state reconciliation |

# 3. Scope of Work

## 3.1 In-Scope Deliverables

Infrastructure Layer

- Proxmox VE cluster integration and management APIs

- ZeroTier network controller and mesh configuration

- Ceph/ZFS storage backend with replication

- Kubernetes cluster provisioning engine

Control Plane Services

- API Gateway with authentication and rate limiting

- Identity and Access Management (IAM) service

- Compute Scheduler and VM lifecycle management

- Network Controller for VPC and connectivity

- Storage Controller for volume and object management

- Billing Engine with usage metering and invoicing

- Observability pipeline for metrics, logs, and traces

User Interfaces

- Tenant Dashboard (Customer Control Plane)

- Super Admin Dashboard (Cloud Operator Plane)

- API documentation and developer portal

## 3.2 Out-of-Scope Items

- Physical datacenter construction or hardware procurement

- Third-party CDN integration

- Bare metal server provisioning (VM-only initially)

- Multi-cloud federation with external providers

- Customer support ticketing system (integration-ready)

# 4. Feature Specifications

## 4.1 User Dashboard - Tenant Control Plane

The Tenant Control Plane represents one isolated cloud universe per customer organization. Tenants have no visibility into infrastructure details, other tenants, or underlying systems.

### 4.1.1 Identity & Organization Management

| Feature | Description |
| --- | --- |
| Organization Management | Create, configure, and manage organizational units |
| Project Isolation | Resource namespacing with quota enforcement |
| User & Service Accounts | Human users and machine identities management |
| RBAC System | Predefined and custom roles with permission sets |
| API Key Management | Token generation, rotation, and revocation |
| SSO Integration | OIDC and SAML provider connectivity |
| Audit Logs | Tenant-scoped activity tracking and export |

### 4.1.2 Compute Services

| Feature | Description |
| --- | --- |
| VM Lifecycle | Create, start, stop, resize, snapshot, clone operations |
| Templates & Images | Golden images and custom OS template library |
| Resource Configuration | CPU, RAM, disk size customization |
| Live Metrics | Real-time CPU, memory, disk, network stats per VM |
| Scheduled Operations | Automated start/stop for cost optimization |
| Placement Rules | Host affinity and anti-affinity specifications |
| GPU VMs | GPU-enabled instance provisioning where available |

### 4.1.3 Container & Kubernetes Services

| Feature | Description |
| --- | --- |
| Managed K8s Clusters | One-click Kubernetes cluster provisioning |
| Node Pool Management | Worker node scaling and configuration |
| Auto-scaling | Horizontal pod and cluster autoscaler integration |
| Cluster Upgrades | Rolling Kubernetes version upgrades |
| Workload Visibility | Namespace and pod status monitoring |
| Container Registry | Integrated private container image registry |
| Resource Quotas | CPU, memory, and storage limits per namespace |

### 4.1.4 Networking

| Feature | Description |
| --- | --- |
| VPC Management | Isolated virtual networks with custom CIDR |
| Subnets & Routes | Network segmentation and routing table config |
| Private Networking | ZeroTier-backed encrypted mesh connectivity |
| Security Groups | Stateful firewall rules for ingress/egress |
| Public IPs | Elastic IP allocation and attachment |
| Load Balancers | L4 (TCP/UDP) and L7 (HTTP/HTTPS) balancers |
| DNS Management | Private and public DNS zone configuration |

### 4.1.5 Storage Services

| Feature | Description |
| --- | --- |
| Block Storage | High-performance persistent volumes |
| Volume Operations | Attach, detach, resize volumes |
| Snapshots & Backups | Point-in-time recovery and backup schedules |
| Object Storage | S3-compatible API for unstructured data |
| File Storage | NFS and SMB shared file systems |
| Encryption | At-rest and in-transit encryption options |
| Cross-Region Replication | Geo-redundant data replication |

### 4.1.6 Platform Services

| Feature | Description |
| --- | --- |
| Managed PostgreSQL | Fully managed PostgreSQL database instances |
| Managed MySQL | Fully managed MySQL database instances |
| Automated Backups | Scheduled database backup with restore points |
| Message Queues | Managed message queue service |
| Event Streams | Real-time event streaming infrastructure |
| Serverless Functions | Go-runtime serverless compute (Phase 2) |

### 4.1.7 Observability & Billing

| Feature | Description |
| --- | --- |
| Metrics Dashboards | Pre-built and custom visualization dashboards |
| Centralized Logs | Aggregated log search and analysis |
| Distributed Traces | Request tracing across services |
| Alerts & Notifications | Threshold-based alerting with integrations |
| Usage Breakdown | Compute, storage, network cost itemization |
| Cost Estimates | Real-time spend tracking and forecasting |
| Budgets & Caps | Spending limits and resource usage caps |

## 4.2 Super Admin Dashboard - Cloud Operator Plane

The Cloud Operator Plane provides omniscient visibility across all tenants, infrastructure, and operations. This dashboard is designed for trained operators managing the entire cloud fabric.

### 4.2.1 Global Tenant Management

| Feature | Description |
| --- | --- |
| Customer Onboarding | New tenant provisioning and configuration |
| Organization Suspension | Account freeze and data retention controls |
| Plan Assignment | Subscription tier and quota management |
| Billing Overrides | Custom pricing and contract adjustments |
| Resource Visibility | Cross-tenant resource utilization view |

### 4.2.2 Data Center Management

| Feature | Description |
| --- | --- |
| Multi-DC Registry | Datacenter catalog with metadata |
| Health Overview | Real-time DC health and capacity metrics |
| Environmental Metrics | Power, thermal, and utilization tracking |
| Maintenance Windows | Scheduled maintenance coordination |
| Region/AZ Definition | Geographic and availability zone mapping |

### 4.2.3 Proxmox Cluster Management

| Feature | Description |
| --- | --- |
| Cluster Registration | Add and configure Proxmox clusters |
| Node Health | Per-node status and performance metrics |
| VM Placement | Visualization of VM distribution |
| Live Migration | Cross-node VM migration orchestration |
| Hardware Inventory | CPU, RAM, disk, GPU cataloging |
| Failure Detection | Automatic node fencing and recovery |

### 4.2.4 Network Fabric Control

| Feature | Description |
| --- | --- |
| Topology Visualization | Network graph with node relationships |
| Inter-DC Links | Datacenter interconnect management |
| Performance Metrics | Latency and throughput monitoring |
| Route Enforcement | Traffic routing policy configuration |
| Traffic Isolation | Tenant network segmentation rules |
| Emergency Isolation | Rapid network quarantine capabilities |

### 4.2.5 Storage Backend Control

| Feature | Description |
| --- | --- |
| Pool Management | Ceph/ZFS storage pool configuration |
| Capacity & I/O | Storage utilization and performance |
| Replication Health | Data redundancy status monitoring |
| Failure Domains | Storage placement group management |
| Backup Policies | Snapshot and backup rule enforcement |

### 4.2.6 Security & Compliance

| Feature | Description |
| --- | --- |
| IAM Policy Templates | Reusable permission policy definitions |
| Secrets Management | HashiCorp Vault integration |
| Certificate Authority | TLS certificate lifecycle management |
| Audit Aggregation | Global audit log collection and search |
| Compliance Reporting | Automated compliance evidence generation |
| Incident Response | Security event investigation tools |

### 4.2.7 Platform Operations

| Feature | Description |
| --- | --- |
| Control Plane Health | Service status and dependency monitoring |
| Service Graph | Microservice dependency visualization |
| Auto-Remediation | Self-healing rule configuration |
| Chaos Testing | Resilience testing triggers |
| Upgrade Orchestration | Rolling platform update management |
| Feature Flags | Dynamic feature enablement controls |

### 4.2.8 Financial & Metering Oversight

| Feature | Description |
| --- | --- |
| Usage Analytics | Global resource consumption analysis |
| Revenue vs Capacity | Financial performance against infrastructure |
| Cost Leakage | Unmetered resource detection |
| Fraud Detection | Abuse pattern identification |
| Custom Pricing | Tenant-specific pricing model configuration |

# 5. Technical Architecture

## 5.1 Architecture Overview

The platform follows a control-plane-centric architecture where all operations flow through centralized services. The architecture is designed to be physically distributed across multiple datacenters while remaining logically centralized for consistent state management.

Core Architecture Principles

- One Control Plane - Single authoritative source for all platform state

- Multiple Authority Scopes - Tenant and operator permissions enforced at API level

- Physically Distributed - Geographic distribution across datacenters

- Logically Centralized - Unified state management and operations

- Security-First - Zero trust, encryption everywhere, minimal privilege

## 5.2 System Layers

| Layer | Components |
| --- | --- |
| Presentation | User Dashboard, Admin Dashboard, API Documentation Portal |
| Gateway | API Gateway, Authentication, Rate Limiting, Request Routing |
| Control Plane | Scheduler, Network Controller, Storage Controller, Billing Engine |
| Coordination | PostgreSQL (State), Redis (Cache), Raft (Consensus) |
| Infrastructure | Proxmox API, ZeroTier API, Ceph/ZFS, Kubernetes |
| Physical | Compute Nodes, Storage Arrays, Network Equipment |

## 5.3 Control Plane Services

| Service | Responsibility |
| --- | --- |
| API Gateway | Request authentication, routing, rate limiting, protocol translation |
| IAM Service | Identity management, RBAC, token validation, SSO integration |
| Compute Scheduler | VM placement, resource allocation, migration orchestration |
| Network Controller | VPC management, firewall rules, DNS, load balancer config |
| Storage Controller | Volume provisioning, snapshot management, replication |
| Billing Engine | Usage metering, cost calculation, invoice generation |
| Cluster Manager | Kubernetes provisioning, node management, upgrades |
| Database Service | Managed DB provisioning, backups, failover |

# 6. Data Flow Design

## 6.1 High-Level Data Flow

All user and administrator operations follow a consistent path through the platform layers. Direct infrastructure access is never permitted from the UI or API layers.

[User / Admin UI] ↓ [API Gateway] ↓ [Auth & IAM Service] ↓ [Control Plane Services] ├── Scheduler ├── Network Controller ├── Storage Controller └── Billing Engine ↓ [Infrastructure Adapters] ├── Proxmox API ├── ZeroTier API └── Ceph / ZFS

## 6.2 VM Creation Flow

| Step | Action |
| --- | --- |
| 1 | User submits VM creation request via Dashboard |
| 2 | API Gateway validates request and routes to Compute Service |
| 3 | IAM Service verifies user permissions and quota availability |
| 4 | Scheduler selects optimal host based on resource and placement rules |
| 5 | Desired state written to Control Plane database |
| 6 | Reconciliation loop detects new desired state |
| 7 | Infrastructure adapter calls Proxmox API to create VM |
| 8 | Network Controller configures ZeroTier membership and firewall |
| 9 | Actual state updated in database, metrics emitted |
| 10 | User receives confirmation with VM details |

## 6.3 Billing Data Flow

| Step | Action |
| --- | --- |
| 1 | Resource metrics collected continuously from infrastructure |
| 2 | Metering service aggregates usage per tenant/project |
| 3 | Usage data stored in ClickHouse for fast analytics |
| 4 | Rating engine applies pricing rules to usage records |
| 5 | Cost data made available for real-time dashboard display |
| 6 | Invoice generator creates billing statements on schedule |
| 7 | Payment integration processes charges if configured |

## 6.4 Failure Handling

| Mechanism | Description |
| --- | --- |
| State Reconciliation | Continuous loops compare desired vs actual state |
| Idempotent Operations | All operations safe to retry without side effects |
| Partial Rollback | Failed multi-step operations reversed automatically |
| Exponential Backoff | Automatic retries with increasing delays |
| Operator Visibility | All anomalies surfaced in admin dashboard |
| Circuit Breakers | Failing integrations isolated to prevent cascade |

# 7. Technology Stack

## 7.1 Backend Services

| Component | Technology |
| --- | --- |
| Primary Language | Go (Golang) 1.21+ |
| Architecture | Microservices with Control Plane pattern |
| Internal Communication | gRPC with Protocol Buffers |
| External API | REST/JSON with OpenAPI specification |
| API Gateway | Custom Go gateway with Envoy sidecar |
| Schema Definition | Protocol Buffers (protobuf) |

## 7.2 Infrastructure Layer

| Component | Technology |
| --- | --- |
| Virtualization | Proxmox VE 8.x |
| Container Orchestration | Kubernetes 1.28+ |
| Software-Defined Networking | ZeroTier + eBPF |
| Load Balancing | Envoy Proxy |
| Block Storage | Ceph RBD |
| Object Storage | MinIO (S3-compatible) |
| File Storage | CephFS / ZFS |

## 7.3 State Management & Coordination

| Component | Technology |
| --- | --- |
| Authoritative State | PostgreSQL 16+ |
| Distributed Coordination | HashiCorp Raft |
| Caching Layer | Redis Cluster |
| Billing & Analytics | ClickHouse |
| Event Streaming | Apache Kafka |

## 7.4 Security Stack

| Component | Technology |
| --- | --- |
| Secrets Management | HashiCorp Vault |
| Workload Identity | SPIFFE/SPIRE |
| TLS Management | cert-manager + custom CA |
| Image Security | Cosign for signing, Trivy for scanning |
| API Authentication | JWT with short-lived tokens |

## 7.5 Observability Stack

| Component | Technology |
| --- | --- |
| Metrics | Prometheus + Thanos |
| Tracing | OpenTelemetry + Jaeger |
| Logging | Loki + Promtail |
| Visualization | Grafana |
| Alerting | Alertmanager + PagerDuty integration |

## 7.6 Frontend Stack

| Component | Technology |
| --- | --- |
| Framework | Next.js 14+ (App Router) |
| Language | TypeScript 5+ |
| Styling | Tailwind CSS 3+ |
| Component Library | shadcn/ui + Radix primitives |
| State Management | Zustand + React Query |
| Real-time Updates | WebSocket with reconnection |
| Charts & Visualization | Recharts + D3.js |

## 7.7 DevOps & Automation

| Component | Technology |
| --- | --- |
| GitOps | ArgoCD |
| CI/CD | GitHub Actions + Tekton |
| Infrastructure as Code | Terraform with custom provider |
| Container Registry | Harbor |
| Configuration Management | Ansible for bare metal |

# 8. Project Phases & Milestones

## 8.1 Phase Overview

| Phase | Name | Duration | Focus |
| --- | --- | --- | --- |
| Phase 1 | Foundation | 12 weeks | Core Infrastructure |
| Phase 2 | Control Plane | 16 weeks | Services & APIs |
| Phase 3 | User Experience | 10 weeks | Dashboards |
| Phase 4 | Platform Services | 12 weeks | Managed Offerings |
| Phase 5 | Production Readiness | 8 weeks | Hardening |
| Phase 6 | Launch & Stabilization | 6 weeks | Go-Live |

## 8.2 Phase 1: Foundation (Weeks 1-12)

Objectives

- Establish development environment and CI/CD pipelines

- Deploy initial Proxmox cluster with basic networking

- Implement ZeroTier mesh networking between nodes

- Set up Ceph storage cluster

- Create infrastructure adapter layer

Deliverables

| Deliverable | Week |
| --- | --- |
| Development environment with GitOps pipeline | Week 2 |
| Proxmox cluster deployment automation | Week 4 |
| ZeroTier network controller integration | Week 6 |
| Ceph storage cluster operational | Week 9 |
| Infrastructure adapter APIs (Proxmox, ZeroTier, Ceph) | Week 12 |

## 8.3 Phase 2: Control Plane (Weeks 13-28)

Objectives

- Build core control plane services in Go

- Implement IAM with multi-tenancy

- Develop compute scheduler and VM lifecycle management

- Create network and storage controllers

- Establish billing and metering infrastructure

Deliverables

| Deliverable | Week |
| --- | --- |
| API Gateway with authentication | Week 15 |
| IAM service with RBAC | Week 18 |
| Compute scheduler and VM management | Week 21 |
| Network controller (VPC, security groups) | Week 24 |
| Storage controller (volumes, snapshots) | Week 26 |
| Billing engine and metering pipeline | Week 28 |

## 8.4 Phase 3: User Experience (Weeks 29-38)

Objectives

- Build tenant dashboard with full feature set

- Develop super admin dashboard

- Implement real-time updates and notifications

- Create API documentation portal

Deliverables

| Deliverable | Week |
| --- | --- |
| Tenant dashboard core navigation and auth | Week 31 |
| Compute and networking UI modules | Week 33 |
| Storage and observability UI modules | Week 35 |
| Super admin dashboard | Week 37 |
| API documentation and developer portal | Week 38 |

## 8.5 Phase 4: Platform Services (Weeks 39-50)

Objectives

- Implement managed Kubernetes service

- Deploy managed database offerings

- Build container registry integration

- Create message queue and event streaming services

Deliverables

| Deliverable | Week |
| --- | --- |
| Managed Kubernetes cluster provisioning | Week 42 |
| Node pool management and auto-scaling | Week 44 |
| Managed PostgreSQL service | Week 46 |
| Managed MySQL service | Week 48 |
| Container registry and message queue services | Week 50 |

## 8.6 Phase 5: Production Readiness (Weeks 51-58)

Objectives

- Security hardening and penetration testing

- Performance optimization and load testing

- Disaster recovery testing

- Documentation and runbook completion

Deliverables

| Deliverable | Week |
| --- | --- |
| Security audit and penetration test report | Week 53 |
| Performance benchmarks and optimization | Week 55 |
| DR testing and failover validation | Week 56 |
| Operational runbooks and documentation | Week 58 |

## 8.7 Phase 6: Launch & Stabilization (Weeks 59-64)

Objectives

- Controlled beta launch with select customers

- Production monitoring and incident response

- Bug fixes and performance tuning

- General availability preparation

Deliverables

| Deliverable | Week |
| --- | --- |
| Beta launch with 3-5 pilot customers | Week 60 |
| Production support handover | Week 62 |
| General availability release | Week 64 |

# 9. Deliverables Summary

| # | Deliverable | Category |
| --- | --- | --- |
| 1 | Proxmox cluster automation scripts | Infrastructure |
| 2 | ZeroTier network controller integration | Infrastructure |
| 3 | Ceph storage cluster deployment | Infrastructure |
| 4 | Infrastructure adapter services | Control Plane |
| 5 | API Gateway service | Control Plane |
| 6 | IAM service with multi-tenancy | Control Plane |
| 7 | Compute scheduler service | Control Plane |
| 8 | Network controller service | Control Plane |
| 9 | Storage controller service | Control Plane |
| 10 | Billing and metering engine | Control Plane |
| 11 | Tenant dashboard application | Frontend |
| 12 | Super admin dashboard application | Frontend |
| 13 | API documentation portal | Documentation |
| 14 | Managed Kubernetes service | Platform |
| 15 | Managed PostgreSQL service | Platform |
| 16 | Managed MySQL service | Platform |
| 17 | Container registry service | Platform |
| 18 | Observability stack deployment | Operations |
| 19 | Security audit report | Security |
| 20 | Operational runbooks | Documentation |

# 10. Assumptions & Dependencies

## 10.1 Assumptions

- Client will provide access to datacenter facilities and network connectivity

- Hardware procurement and physical installation is managed by client

- Minimum of 3 physical nodes available for initial Proxmox cluster

- Dedicated development and staging environments available

- Technical stakeholders available for weekly progress reviews

- Change requests will follow formal change control process

- Production domain names and SSL certificates provided by client

## 10.2 Dependencies

| Dependency | Owner | Required By |
| --- | --- | --- |
| Physical server hardware | Client | Phase 1 Start |
| Network infrastructure (switches, routers) | Client | Phase 1 Week 2 |
| Internet connectivity with public IPs | Client | Phase 1 Week 4 |
| Storage hardware (SSDs, HDDs) | Client | Phase 1 Week 6 |
| DNS zone delegation | Client | Phase 3 Start |
| SSL wildcard certificates | Client | Phase 3 Week 2 |
| Payment gateway credentials | Client | Phase 5 Start |
| Beta customer agreements | Client | Phase 6 Start |

## 10.3 Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Hardware delivery delays | High | Early procurement, buffer in schedule |
| Integration complexity | Medium | Proof-of-concept before full build |
| Scope creep | High | Formal change control, clear requirements |
| Key personnel availability | Medium | Knowledge sharing, documentation |
| Security vulnerabilities | High | Security-first design, regular audits |
| Performance issues at scale | Medium | Load testing from Phase 3 |

# 11. Acceptance Criteria

## 11.1 Functional Acceptance

- All features specified in Section 4 demonstrably functional

- API endpoints match OpenAPI specification with 100% coverage

- UI workflows complete end-to-end without errors

- Multi-tenancy isolation verified through security testing

- Billing accuracy validated against test scenarios

## 11.2 Performance Acceptance

| Metric | Threshold |
| --- | --- |
| API response time (p95) | < 200ms |
| VM provisioning time | < 60 seconds |
| Dashboard page load | < 2 seconds |
| Concurrent users supported | > 500 |
| System availability | > 99.9% |
| Failover time | < 30 seconds |

## 11.3 Security Acceptance

- No critical or high severity vulnerabilities in penetration test

- All data encrypted at rest and in transit

- RBAC enforcement verified across all API endpoints

- Audit logs capture all administrative actions

- Secrets management follows industry best practices

## 11.4 Documentation Acceptance

- API reference documentation complete and accurate

- Administrator guide covers all operational procedures

- User guide explains all tenant dashboard features

- Runbooks available for all common operational scenarios

- Architecture documentation reflects as-built system

# 12. Terms & Conditions

## 12.1 Change Control

All changes to scope, timeline, or deliverables must be submitted through the formal Change Request process. Changes will be evaluated for impact on schedule and budget, with written approval required before implementation.

## 12.2 Intellectual Property

Upon full payment, all custom-developed code and configurations become the property of the Client. Third-party open-source components remain subject to their respective licenses. Vendor retains rights to reusable frameworks and methodologies.

## 12.3 Warranty

A 90-day warranty period begins upon General Availability release. During this period, defects in deliverables will be corrected at no additional cost. Warranty does not cover issues arising from client modifications or third-party integrations.

## 12.4 Confidentiality

Both parties agree to maintain confidentiality of proprietary information shared during the project. This obligation survives project completion and continues for a period of three years.

ACCEPTANCE

By signing below, both parties acknowledge acceptance of this Statement of Work and agree to the terms and conditions contained herein.

— End of Document —